## TTD
Test Case ID | User Story ID | Acceptance Condition | Preconditions | Test Data | Steps/Instructions | Expected Results | Actual Results | Pass/Fail | Notes | Image Proof | Extra | Imgur link
1 | None | front end test code loads correctly | Webpage loads basic HTML/CSS/JS elements | console.log hello world + css aqua | Link files to HTML for loading | bg color change, and console log showing correct test data | JS loaded fine, CSS body code was wrong | pass | Changed css to correct code, and all loads fine | https://imgur.com/xmqq2ry |  | https://imgur.com/a/mbbmrYf
2 | 7 | Font Loads as calibri, has a fixed text size and is centered horizontally | A h1 tag needs to be in place to be centered and to check the font | User Data | Change document wide css to make font correct + center it | nice text | Looks sicko | pass | Wasn’t actually sure what calibri looked like, and had to double check online | https://imgur.com/lJt64tf
3 | 7 | the div with user input form needs to match wireframe colors | Needs form html tags in place, inside of a div | none | Add bg in css | Background Change | Didn’t change into given color | fail | used an eyedropper color, which wasn’t given in brief, so changed. Also think the ID name of the div was wrong EDIT: rgb color wasn’t correct syntax | https://imgur.com/vHtYIKo
4 | 1,2,3 | Areas of for user input need to be added and interactable | Form needs to be added to HTML file | input fields are labeled correctly and 1a! Can be put into all 3 | Create a form with 3 input fields, labeled in the HTML document | All would be interactable and visible | Form was added fine, but formatting was weird, so needs CSS changes | pass |  | https://imgur.com/2QC8t1U
5 | 7 | Being able to identify what is/isnt being effected by background colors | Case ID 3 conditions | Random rgb values | input random rgb values into form background image, as well as body background to troubleshoot bg issue | backgrounds of both body and divs should change | successfully changed colors properly | pass |  | https://imgur.com/4achozX
6 | 7 | Form details need to be stacked vertically | form elements need to be in place | none | add css code to stack the input fields | The form elements to stack properly | I was having a lot of issues with stacking elements, but realised the answer was in the HTML, instead of CSS | pass | In the end I had to change elements to label sections next to input forms. Also messed around with the colors and css layout. See pics for more details | CSS | HTML
7 | 14 | Submit button sends something to email | submit button added and a valid email to be used for sending information | Using my test email instead of given brief one (will change if this works) | use form submit button to send anything | should open mail window to send an email (using windows) | nothing happened | fail | Form settings need changing | https://imgur.com/scbZorC
8 | 14 | Submit button sends something to email | submit button added and a valid email to be used for sending information | Using my test email instead of given brief one (will change if this works) | use form submit button to send anything | should open mail window to send an email (using windows) | Sends data to an email to be sent to user | fail | Using my trusty friend google, I found out I needed to change the form action to 'mailto:email'. Unfortunately no data is added to the email, but I think this is an easily solvable issue with the form settings | https://imgur.com/Zx59B0g
9 | 14 | Submit button sends something to email | Need a PHP script to take the given data and send it to a user | Using my test email | using script from: https://html.form.guide/email-form/html-email-form/ I will make the form action send an email through PHP | should open mail window to send an email (using windows) | Would open a new tab with my PHP Code | fail | Don’t think this is the way to go. Apparently you need a server or client side hosting 'thing', and since it wasn't specifically specified this just intuitively feels wrong. Also I have no idea what I'm doing with it.
10 | 14 | Submit button sends something to email | submit button added and a valid email to be used for sending information | Using my test email instead of given brief one (will change if this works) | use form submit button to send anything | should open mail window to send an email (using windows) | Sends data to an email to be sent to user | pass | Added a bit to the mailto action in HTML, that sets input as body text, but includes HTML code which isn't ideal, but technically a success. I think this is something to solve with JavaScript, when I actually get there (saving until basic framework is fully in place ) | https://imgur.com/1Ls3ar9
11 | 13 | Webpage follows wireframe in mobile view | Page is correctly setup beforehand with css and HTML elements | none | Using dev tools, check page in mobile view | DOM elements will scale properly | Input text boxes broke through div margins | fail | Need to adjust border widths | https://imgur.com/wTMuL3I
12 | 13 | Webpage follows wireframe in mobile view | Page is correctly setup beforehand with css and HTML elements | none | Using dev tools, check page in mobile view | DOM elements will scale properly | Changed margin sizes to achieve a normal scaling effect | Pass | When the page is in desktop (in larger views), because I am using % scaling, it will reach to the sides quite far. I don’t think this looks particularly bad, but would understand if this is something undisired in the final result | https://imgur.com/wdo49AW
13 | 8 | Javascript action listener should detect use of the submit button | Submit button and javascript actionlistener need to be present | console.log("HELLO :)"); | After adding function, check submit button produces test data in console | hello in console | Console window epxlaining wrong syntax | fail |  | https://imgur.com/O9AQ81t
14 | 9 | Javascript action listener should detect user click input | javascript actionlistener needs to be present | console.log("HELLO :)"); | After adding function, check submit button produces test data in console | hello in console | Shows hello, but no functionallity. | fail | Text loads when script loads. Believe this could be due to loading in the head, instead of body but also could be due to the way I have made the function | https://imgur.com/GCRzhH9
15 | 10 | Javascript action listener should detect user click input | javascript actionlistener needs to be present | console.log("HELLO :)"); | While using an eventlistener function found online click on the screen | hello in console | Produces hello in console when clicked anywhere on document | pass | I think I was trying to incorporate one of these =>, since it was what I used last time. Also code is from w3schools | https://imgur.com/2cPukwi
16 | 10 | Javascript action listener should detect use of the submit button | javascript actionlistener needs to be present | console.log("HELLO :)"); | After editing old function, check submit button produces test data in console | hello in console | Produces hello in console when submit button is clicked | pass |  | https://imgur.com/QVmL1EK
17 | 10 | All fields detect user input (click) | actionlisteners + html elements | console.log("HELLO :)"); | Add all eventlisteners to all inputs | hello in console for each input clicked on | All fields produce hello when clicked | pass | Used an array and looped through to add event listeners to each. Think this might need changing for code readablity, since userElement[1] isn't very descriptive | https://imgur.com/DJJxcTA
18 | 10 | All fields detect user input (click) | actionlisteners + html elements | console.log("HELLO :)"); | Add all eventlisteners to all inputs | hello in console for each input clicked on | All fields produce hello when clicked | pass | Changed array to an object with help from https://masteringjs.io/tutorials/fundamentals/foreach-object to add event listeners, while keeping code easier to read | https://imgur.com/EDmnBzc
19 | 10 | All fields detect all user input | actionlisteners + html elements | 123 | Write test data into fields while checking console window to see if it is detecting input | shows 123 in console | Showed object names & doesn’t respond to input events | fail |  | https://imgur.com/kzrrqLH
20 | 10 | Function for checking input needs to correctly corrospond to input | actionlisteners + html elements | 123 | Write test data into fields while checking console window to see if it is detecting input | shows 123 in console | not responding to input, only the name of the field on loading | fail |  | https://imgur.com/kBHIZPq
21 | 10 | Function for checking input needs to correctly corrospond to input | actionlisteners + html elements | 123 | Write test data into fields while checking console window to see if it is detecting input | shows 123 in console | not responding to input, only the name of the field on loading | fail | Need to recheck how JS actionlistener syntax is written, as I believe I was too confident in my knowledge before writing this | https://imgur.com/LFvOmV8
22 | 10 | Function for checking input needs to correctly corrospond to input | actionlisteners + html elements | Hello world | Write test data into fields while checking console window to see if it is detecting input | shows hello world | responds to input, but doesn’t show specific input values | pass | Need to change what the function outputs, but am on the right track. | https://imgur.com/8vWM8Ca
23 | 10 | All fields detect all user input | actionlisteners + html elements | 123 | Write test data into fields while checking console window to see if it is detecting input | shows 123 in console | Shows the last input used, but not the entire string, which will be needed for checking validity | pass | Only shows one value, instead of whole string. This could be added to an array to be checked, but seems redundant when it should be in the field objects data | https://imgur.com/EKuiOEv
24 | 10 | All fields detect all user input | actionlisteners + html elements | 123 | Write test data into all fields while checking console window to see if it is detecting input | shows 123 in console for each field | Now shows whole string in console of name field input, but not the others | fail | Realised this is checking event data, not object data. Will need to either loop through each object input value or hard code it in each one. | https://imgur.com/83KhElj
25 | 10 | All fields detect all user input | actionlisteners + html elements | 123 | Write test data into all fields while checking console window to see if it is detecting input | shows 123 in console for each field | Console shows all fields with all data (though is hard to read) | pass | was correct :) | https://imgur.com/eXQwCDl
26 | 10 | All fields detect all user input | actionlisteners + html elements | 123 | Write test data into all fields while checking console window to see if it is detecting input | shows 123 in console for each field | Console shows all fields with all data (though is hard to read) | pass | Streamlined code and made it better and stuff | https://imgur.com/QYkbz88
27 | 11 | ASCII Keycodes are read correctly | User input detection + keycode check function | 123 | Write test data into all fields while checking console window to see if it is detecting Ascii keycodes | Keycodes for 123 shown in console | Shows error message | fail | Created an array for each banned ascii character within the standard printable character range which is ().;:<>[\]^. I think my error in this case is just a syntax issue, but will try with the characters instead to see if my method actually works | https://imgur.com/Oqg8LhL
28 | 11 | string characters are read correctly | User input detection + keycode check function | 123 | Write test data into all fields while checking console window to see if it is detecting Ascii keycodes | Keycodes for 123 shown in console | Shows characters at each index of the user input fields when interacting | pass | Now just need to convert to ascii keycodes | https://imgur.com/ZgFV0oQ
29 | 11 | ASCII Keycodes are read correctly | User input detection + keycode check function | 123 | Write test data into all fields while checking console window to see if it is detecting Ascii keycodes | Keycodes for 123 shown in console | shows each ascii keycode in | pass | Used CharCodeAt to get the keycode of the index. Am going to compare this to https://theasciicode.com.ar/ for the keycode refrence | https://imgur.com/tLsAdYW
30 | 11 | ASCII Keycodes are the same as the ones used in my banned keycode array | Array of banned keycodes + input detection in each field | ().;:<>[\] | Write test data into a field and see if it corresponds to the data given online and in array | Keycodes Match | Keycodes Match | pass | Done to check if the online resources matched up. I have had issues in the past of these not matching up, so this was just a double check | https://imgur.com/ReSUVx0
31 | 11 | Convert function to one that checks and compares values to keycodes | Function with a for loop to detect if array elements are the same as characters in user inputs | 12^ | input test data and see if console warns of issue | Warns you when a banned keycode is present | Warns you when a banned keycode is present | pass | Surprised it worked 1st try, now will try seeing if using a keycode outside of accepted 32-126 range will produce unexpected results | https://imgur.com/K0YAu30
32 | 11 | keycodes outside of 32-126 range are console logged as bad | Function with a for loop to detect if user inputs are outside of given range | Ç | input test data in field, and see if console admits to wrongdoings (general evilness) | console logs that input is out of range | console didn’t let me know :( | fail | Think I need to change my if statement to be &&, as well as making the range tighter (is > 32 & <127 at the moment) | https://imgur.com/9A76Mbb
33 | 11 | keycodes outside of 32-126 range are console logged as bad | Function with a for loop to detect if user inputs are outside of given range | Ç | input test data in field, and see if console admits to wrongdoings (general evilness) | console logs that input is out of range | The console did let me know what keycode wasn’t in the acceptable range | pass | The ascii keycode described on the website (website was 128, instead of 199) didn’t match up to the one given by JavaScript, so either the website is wrong, or I'm using some other kind of keycodes without realising | https://imgur.com/2CxEYA8
34 | 11 | keycodes outside of 32-126 range are console logged as bad | Function with a for loop to detect if user inputs are outside of given range | Ç | input test data in field, and see if console admits to wrongdoings (general evilness) | console logs that input is out of range but corrosponds to keycode data | The console did let me know what keycode wasn’t in the acceptable range but still gave unexpected results | fail | I also managed to accidently open the mail, and found out that certain printable characters when put into the text of the email body are very odd. I believe these are escape characters so that the \ and / don’t effect the HTML. Also using https://www.toptal.com/developers/keycode, I can see that the keycodes are wildly different from what I expect, yet my code still works properly so am genuinely unsure of what is causing this issue. | https://imgur.com/BJNZBub
35 | 11 | keycodes outside of 32-126 range are console logged as bad | Function with a for loop to detect if user inputs are outside of given range | keycodes out of acceptable ranges from https://www.rapidtables.com/code/text/ascii-table.html | input test data in field, and see if console admits to wrongdoings (general evilness) | console logs that input is out of range but corrosponds to keycode data | The corrosponding values are correct from here. | pass | Issues arose from not realising that the online keycodes are from event values, instead of the actual ASCII keycodes, which actually were correct when being analysed by charCodeAt | https://imgur.com/wT1yL0C
36 | 11 | Class values are visible by console for an input field | Class template for user input to hold the data for the: dom element + its value, its given name and weather its valid | "name",document.getElementsById("name") | Create a class with given parameters defined in constructor | console should log class name validity and type of DOM used | Error at the constructor peramaters given. | fail | Believe that the document.getId should probably instead use the JSON data, however I was planning to get rid of this if the classes worked, since this data could be stored there instead | https://imgur.com/NXmpKYx
37 | 11 | Class values are visible by console for an input field | Class template for user input to hold the data for the: dom element + its value, its given name and weather its valid | "name",document.getElementsById("name") | Create a class with given parameters defined in constructor | console should log class name validity and type of DOM used | Sucessfully shown correct names and document element | pass | Isssue was bad syntax. Used to making classes in c#, which sets constructor name to be the same as the class. | https://imgur.com/JMNknMS
38 | 11 | Class values are visible by console for an input field while using JSON data | Class template for user input to hold the data for the: dom element + its value, its given name and weather its valid | "name",fields.name | Create a class with given parameters defined in constructor | console should log class name validity and type of DOM used | Worked same as above | pass | Just to check this method works | https://imgur.com/6rWObKq
39 | 11 | Successful addition of action listeners to class types | input class with defined input field | 123 | add event listener to a new input field class, using its _type attribute | console log works same as before adding classes (logging input text | mirrored old code perfectly and showed input text in console | pass | Was surprised this worked, but will create an array of these classes | https://imgur.com/rgg9jOC
40 | 11 | Successful addition of action listeners to all class types | input class with defined input field | 123 | add event listener to a new input field class, using its _type attribute | console log works same as before adding classes (logging input text | mirrored old code perfectly and showed input text in console | pass | This was to update each input class to have an action listener | https://imgur.com/KQn56H1
41 | 11 | successful addtion of input fields being added to an object | inputs field with defined classes for each input | 123 | add inputfield classes in place of old documentIds within fields object | console log works same as before adding classes (logging input text | Showed error message on load | pass | Syntax issue | https://imgur.com/lbKqobY
42 | 11 | successful addtion of input fields being added to an object | inputs field with defined classes for each input | 123 | add inputfield classes in place of old documentIds within fields object | console log works same as before adding classes (logging input text | No error message showed on load, and worked the same as previously | pass |  | https://imgur.com/uCZktUC
43 | 11 | conversion of keycode check in console works as intended with classes | classes with actionlisteners for each input field | 123 | input 123 into test field, and see if console logs it | On each input, logs the data within the field | shows error message each input | fail | This needs to be put inside of the class, and also was trying to read values from the old inputs object (which now has classes instead of document.getId's) | https://imgur.com/dz8aeBq
44 | 11 | successful read of a value of the inputfield class logged to the console | funtction within the class that reads the value of the inputfield | 123 | input 123 into test field, and see if console logs it | console log works same as before adding classes (logging input text | worked the same as before (after lots of trial and error) | pass | This took me a very long time, and still am unsure of why using.value works. Was trying to use _type.value, but that would always show up as undefined in console. Should've made lots of test cases for this, but didn’t want to overload this document with the same test + was brute forcing ideas and got carried away :/ | https://imgur.com/qW3KFh8
45 | 11 | conversion of keycode check in console works as intended with classes | classes with actionlisteners for each input field | 123 | input 123 into test field, and see if console logs each keycode | On each input, logs the data within the field | successfully logged the keycodes, same as previously | pass | Had to restructure the code a bit, and put the invalid keys within the ascii check method. | https://imgur.com/rECWBpZ
46 | [6 empty] | Email still sends when all fields have input | pass |  | https://imgur.com/eQ203V1
47 | [6 empty] | submit button class works | pass | showing type so I can see what is being accessed | https://imgur.com/S9MfqFY
48 | [6 empty] | All input fields still work | pass | console still is functional | https://imgur.com/c6GvlDw
49 | [6 empty] | shows undefined type on submit | fail | messed up foreach on the object lists | https://imgur.com/lbcwNta
50 | [6 empty] | loads email despite all classes showing a false _valid value | fail |  | https://imgur.com/4LvbvcB
51 | [6 empty] | true was only set when changed outside of the classes method. | pass |  | https://imgur.com/36t79ym
52 | [6 empty] | Import of luhn function worked fine | pass |  | https://imgur.com/mtwREAT
53 | [6 empty] | email field detected @ and . | pass |  | https://imgur.com/mUvbhQv
54 | [6 empty] | background wasn’t changing to correct color in email despite all fields being valid | fail |  | https://imgur.com/5RoySNu
55 | [6 empty] | Color does correctly change for name | pass |  | https://imgur.com/Oosbzc4
56 | [6 empty] | Color does correctly change for email | pass |  | https://imgur.com/HrMrPJS
57 | [6 empty] | Color does correctly change for card | pass |  | https://imgur.com/6kcZeHL
58 | [6 empty] | switch statement works | pass |  | https://imgur.com/mBR56k3
59 | [6 empty] | successful validation of data | pass |  | https://imgur.com/DCXIUy0
60 | [6 empty] | no body data inside of email but email sending was possible with JS | pass |  | https://imgur.com/4F6s6gC
61 | [6 empty] | body data can be manually set | pass |  | https://imgur.com/PmqWTqN
62 | [6 empty] | Variable data was set to body text in email | pass |  | https://imgur.com/PXKDzo2
63 | [6 empty] | email sent | pass |  | https://imgur.com/XJGbTRS
64 | [6 empty] | Colors in brief are bad/wrong | fail |  | https://imgur.com/oMHzmMy
65 | [6 empty] | Another email sent | pass |  | https://imgur.com/SIUYr5R
66 | [6 empty] | successful asp.net MVC template created | pass |  | https://imgur.com/SIV6pDh
67 | [6 empty] | Successfully launched template build | pass |  | https://imgur.com/tAwIe0w
68 | [6 empty] | Changed HTML text in default welcome screen | pass |  | https://imgur.com/KMOuIVt
69 | [6 empty] | Changed Head data | pass |  | https://imgur.com/ZQb3X2i
70 | [6 empty] | Successfully loaded data through direct webpage input in adress bar | pass |  | https://imgur.com/CfYV3Qk
71 | [6 empty] | Loading of custom index View file failed | fail |  | https://imgur.com/6xxmFES
72 | [6 empty] | Loading of custom index View file was successful | pass |  | https://imgur.com/iAtAikc
73 | [6 empty] | Welcome view file was successfully loaded using Controller features | pass |  | https://imgur.com/1ITNHEv
74 | [6 empty] | Successfully changed default controller to load | pass |  | https://imgur.com/OobvCWF
75 | [6 empty] | successful change of basic data in nav bar | pass |  | https://imgur.com/Z7QJDZt
76 | [6 empty] | successful css import | pass |  | https://imgur.com/upaIlm9
77 | [6 empty] | successful HTML import | pass |  | https://imgur.com/xl92lVa
78 | [6 empty] | successful refrencing of css to html elements | pass |  | https://imgur.com/aRNYjCO
79 | [6 empty] | Javascript Load Error | fail |  | https://imgur.com/EYVTSgQ
80 | [6 empty] | Javascript loaded successfully | pass |  | https://imgur.com/GIZJDzE
81 | [6 empty] | js validation works | pass |  | https://imgur.com/85vcA7l
82 | [6 empty] | Email Loads Successfully | pass |  | https://imgur.com/lPNGfDu

## User Stories
ID | Stakeholder | User Story | ID | User Story ID | Issue/defect | Assumption
1 | commercial director | As a user I need to be able to insert my name into the form | 1 | 1 |  | Going to use HTML forms instead of individual elements in a div
2 | commercial director | As a user I need to be able to insert my email into the form | 2 | 2 |  | Going to use HTML forms instead of individual elements in a div
3 | commercial director | As a user I need to be able to insert my Credit/Debit Card into the form | 3 | 3 |  | Going to use HTML forms instead of individual elements in a div
4 | commercial director | As the Commercial Director I need users to only be able to enter valid names | 4 | 4 | What counts as a valid name? | Names would just be anything from 2-20 characters long
5 | commercial director | As the Commercial Director I need users to only be able to enter valid email address | 5 | 5 |  | Validity would be checked during user input to adhere with CTO case ID 9. Checks specifically for an @ symbol, and within the 2-20 character range
6 | commercial director | As the Commercial Director I need users to only be able to enter valid credit card | 6 | 6 |  | Validity would be checked during user input to adhere with CTO case ID 9 + LUHN algorithm as mentioned down below
7 | Marketing director | As the marketing director I need the page to conform to our branding guidelines and use our brand colours: Green RGB 137,200,46 Hex 89c82e Grey RGB 60,60,59 Hex 3c3c3b Pink RGB 231,0,100 Hex 700064 | 7 | 7 | Think this could clash with UX design &/or accessability stuff | Assuming this is the DN colors listed given by CTO in user story 9
8 | commercial director | As the marketing director I need the page to be consistent with our other pages i.e., using the same Calibri font and text size, centred horizontally and vertically | 8 | 8 | Don’t know how other pages look | Using visual wireframe and given info as reference. Styling will be in css sheet.
9 | CTO | As CTO I need the application for follow our UX (User Experience) guide so that each user has the best possible experience. This should include any issues being highlighted to the user when they are still entering a field of as soon as possible after. Correct fields should be shown as DN green, errors shown in DN Pink. | 9 | 9 | UX Guide not avalible :0
10 | CTO | As CTO I need to ensure that any data capture is secure and there is no risk of database corruption through SQL injection. Only standard upper / lower case. letters and printable characters: !#$%&'*+-/=?^_`{¦}~ should be allowed in all fields. | 10 | 10 | Is user allowed to put this into forms at all? | Checking every input at runtime seems excessive, but will add event listners at all input fields.will show error message if input contains satan characters.
11 | CTO | As CTO I need to ensure that all accepted credit cards conform to the LUHN algorithm | 11 | 11 | Need to relearn what the algorithm is lol | Test data will need to conform, so must use a fake number & test multiple types
12 | CTO | As CTO I need to ensure that all applications can run on all common browsers, devices and screen sizes. | 12 | 12 | Devices not specified | Website should work on any browser/desktop, IOS and android, so will test with my own devices (android and chrome) Chrome dev tools also have a mobile view that I will consistently compare and view.
13 | CTO | As CTO for this exercise, I need an Email to test@dn-uk.com be sent containing the validated information when a user presses a ‘Submit’ button. | 13 | 13 | Doesn’t seem secure if we were to use real details. Also generally unsure of how to carry this out | Will only use valid test data to send email.
14 | CTO | As CTO I need to ensure all applications can be accessed by all users, the application needs to conform to w3c accessibility initiative. | 13 | 14 | Method of sending emails can vary (could use php but not in scope of assignment) | will use php as a last resort (since I don’t really know it), but will look for various solutions. EDIT: basically HTML has a built in thing for the forms, so will be using that.
|  |  | 14 | 10 | Emails Include @ and . Symbols, which are unspecified. Also not sure if there is a grammar error, as the listed printable characters are essential for SQL Injections | Will check for ascii UTF-8 Valid characters only (charcodes 32-126). Will also exclude keycodes for the characters ().:;<>[\]^